## Slide 1: Session 1: Understanding the past and anticipating the future Overview of the new workplan
Production of Skills Supply and Demand Forecasts
Rachel Beaven, Cambridge
Econometrics
Skillsnet Technical Workshop, 24-25 November 2016, Thessaloniki
CEDEFOP
Alphametrics

## Slide 2: Overview of the new workplan
The new Framework Contract
Overview of approach
Improvements & developments
Workplan

## Slide 3: The new Framework Contract
Requirement: Production of skills supply and demand forecasts
  the rationale for regular skills projections, and Cedefop’s models and processes, are now well established
Duration: July 2016 – June 2020
Our team
  many familiar faces
  CE is now the lead contractor, responsible for overall project management, coordination and liaison with Cedefop, partners, sub-contractors, ICEs and CGEs

## Slide 4: Overview of approach
Regular updates to the Core Projections required to meet Cedefop’s minimum requirements
Improvements and developments to the approach, including
  ‘incremental’ improvements emerging from lessons learned during the previous framework contracts
  substantial developments, such as, exploring the feasibility of extending the analysis and projections to the 3-digit level of ISCO08
  enhancements to dissemination

## Slide 5: Regular updates
Data | Source | Input to which Module in Cedefop’s framework | Release date and/or changes to methodology
Historical data |  |  | 
Economic | National Accounts (Eurostat) | 1 Macro model | Releases throughout the year. No methodological changes announced or expected (e.g. NACE and ESA)
Employment demand by sector | National Accounts (Eurostat) | 1 Macro model | 
Population | Eurostat | 1 Macro model | 
Participation rates | Eurostat | 1 Macro model | 
Unemployment | AMECO (DG ECFIN) | 1 Macro model | Released twice a year in Spring and Autumn.
EU-LFS | Eurostat | 1 Macro model 2 & 3 Expansion demands 4 Replacement demand 5 Qualification supply | Usually released in April or May of each year.
Projections |  |  | 
Economic (short-term) | AMECO (DG ECFIN) | 1 Macro model | Released twice a year in Spring and Autumn
Demographic | EUROPOP (Eurostat) | 1 Macro model | 2016 and 2019 (expected every three years) no exact release dates. The 2016 ESTAT workplan suggest dissemination of new projections in the first half of 2017.
Economic (long-term) | Ageing Report (DG ECFIN) | 1 Macro model | Close to new EUROPOP release date. Usually published a few months after the population forecast release. Outlines methodology & assumptions.

## Slide 6: Regular updates
Full update in 2017/18
  existing models will be reviewed and re-estimated, using revised data
    new EUROPOP projections expected
    recent economic developments (including Brexit vote)
    additional years of ISCO08 data
  optimistic and a pessimistic scenarios
  timescales
    summer 2017: checking preliminary results
    autumn 2017: validation workshop
    early 2018: publication
Other updates
  Fast update in 2018/19
  Full update in 2019/20

## Slide 7: The role of Individual Country Experts
Contribution | ICE task | Team response
Scrutiny and validation of the forecast results - baseline | Structured questionnaire - review initial assumptions for GDP projections (inputs to Module 1 E3ME) | CE adjustments to the assumed GDP projections
 | Structured questionnaire - review intermediate results: E3ME: sectoral employment; labour supply; and unemployment | CE adjustments in E3ME
 | Questionnaire (integrated with Country Workbooks) - review intermediate results: skill demand results, including occupational and qualification shares | IER adjustments in Country Workbooks
 | Questionnaire (integrated with Country Workbooks) - review intermediate results: skill supply results (qualification shares) | 
 | Sessions at Skillsnet Workshops – discuss and feedback on country-specific results | CE and others, adjustments as above
Scrutiny and validation of the forecast results - scenario | Structured questionnaire - review initial design of scenario and the associated assumptions | CE and others, refinements to scenario design and assumptions
 | Structured questionnaire - review and sense-check emerging findings and narrative | CE and others, investigation/clarification of results, refine scenario and narrative
 | Sessions at Skillsnet Workshops – discuss and feedback on scenario assumptions and country-specific results | 
Peer review and validation of the methods and sources | Sessions at Skillsnet Workshops – discuss and feedback on existing methods and sources, and proposed methodological developments | CE and others, collate and consider ICE comments. Make prioritised recommendations (for discussion with Cedefop) for improvements and developments to the methods and sources.

## Slide 8: Improvements and developments
Model developments
  detailed analyses of occupations and qualifications
  linking occupational (replacement) demand to supply indicators
  alternative treatment of skills supply: pseudo-cohort modelling of qualifications transitions
Improvements to process
  data outputs
  dissemination

## Slide 9: Modelling framework
Module 1: Multi-sectoral macroeconomic model (E3ME)
Employment (labour demand)
Labour market participation rates
Benefit rates
Economic activity
Active labour force by age and gender
Working age population by age and gender (exogenous)
Unemployment
Wage rates
Job openings by Occupation(ISCO 2 digit)
Job openings by
Qualification
(ISCED category)
Module 2: Employment levels and Expansion Demand by occupation (EDMOD)
Module 3: Employment levels and Expansion Demand by qualification (QUALMOD)
Module 4: Replacement demand by occupation / qualification (RDMOD)
Module 6: Stocks & Flow numbers by ISCED category (STOCKFLOWMOD)
Numbers in the population by ISCED category
Module 5: Stocks of people by qualifications, 3 ISCED levels & by economic status (STOCKMOD)
Module 7: Imbalances (Supply-Demand), 3 ISCED levels (BALMOD)
Numbers in the labour force by ISCED category
Supply of skills
Demand for skills
Module 8: Occupational Skills Profiles (OSPs)
Notes: Talk through in brief

## Slide 10: Work plan
Key task | Activity | Responsible | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  | 
Core Projections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | Extension of EU-LFS database and analysis to use field of study | AM & WIIW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Development and refinement of the methodology for occupational and qualification projections | IER, AM & WIIW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Extending the analysis to occupations by 3-digit ISCO | IER, AM & WIIW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Replacement demand: consolidation of methods to incorporate ISCO08 | ROA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Replacement demand: robustness/sensitivity analysis of retirement and outflow rates assumptions | ROA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Qualification supply: adapt stock-flow models to make use of pseudo-cohort data | IER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Imbalances indicators: include fields of study | ERC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | Review existing data sources and create/update relevant databases with most recent data, including indication of measures for adjusting them if necessary | CE, AM & WIIW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Produce skills demand and supply forecast (baseline scenario) with scope of results as described in Section 2.4.3 of the Tender Specifications. | CE & all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Examine the consistency of the results with the previous Cedefop forecasts | CE & IER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Produce two alternative macroeconomic scenarios (optimistic and pessimistic) | CE & IER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Workshops and meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Skillsnet annual validation workshops | CE & all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Notes: Table 3.6 from the bid

## Slide 11: Summary
Regular updates to the Core Projections required to meet Cedefop’s minimum requirements
  Full update in 2017/18
  Fast update in 2018/19
  Full update in 2019/20
To be prioritised are many improvements and developments to the approach, including
  ‘incremental’ improvements emerging from lessons learned during the previous framework contracts
  substantial developments, such as, exploring the feasibility of extending the analysis and projections to the 3-digit level of ISCO08
  enhancements to dissemination

## Slide 12: Further information
Cambridge Econometrics
Eva Alexandri, ea@camecon.com
Rachel Beaven, rb@camecon.com
E3ME model www.e3me.com